## About database
Annex 3
Project „Water bodies without borders” (EstLat 66)
INTRODUCTION TO THE DATABASE FOR PROGRAM OF MEASURES
Disclaimer: This document reflects the views of the authors. The managing authority of the programme is not liable for how this information may be used.
Explanations of table columns
Water body information | WB Code | Water body code
| WB Estonian name | Water body name in Estonian. Both Estonian and Latvian names are given only for transboundary waterbodies.
| WB Latvian name | Water body name in Latvian. Both Estonian and Latvian names are given only for transboundary waterbodies.
| Transboundary WB code | Transboundary water body harmonized code
| Country | Name of the country
| County | Name of the county
| Municipality | Name of the municipality
Status information 2019 | Status 2019 | Last available status information, 2019.
| Not good status element, 2019 | Not good status element according to latest status assessment.
| Reason for the not good status | Reason for not good status according to latest status assessment; see also row 44 and onwards.
| Monitoring year (latest or not monitored) | Latest year that waterbody has been monitored or not monitored at all.
| Status assessment confidence level | Status assessment confidence level shows what kind on information is available (biological quality elements and other supportive conditions) on each waterbody for assessing ecological status: 0 - no information, 1 - low, 2 - medium, 3 - high).
Pressures information 2019 | Water use causing failure of good ecological status/good ecological potential (GES/GEP) | Name of the water use that is causing failure of good ecological status/good ecological potential.
| What causes the load: sector/water user | Name of the sector that is causing the load.
| GAP | The gap between status 2019 and good status.
Existing measures from 2015-2021 river basin management plan | The purpose of measure | the purpose of the measure shows the pressure that has to be minimized by measures.
| Code of measure | Code of measure
| Type of measure | Type of measure: administrative, technical, consulting, study.
| supplementary, additional measure | Supplementary or additional measure
| Measure | Name of the measure
| Responsible partner for implementing the measure | Name of responsible partner for implementing the measure.
| not implemented / in progress | Information on the implementation of the existing measure.
| End of implementation | Information on the due date of implementation existing measure.
Additional measures | Type of measure | Type of measure: administrative, technical, consulting, study.
| Code of measure | Code of measure
| Measure | Name of the measure
| Description of measure | Description of measure
| Responsible partner for implementing the measure | Name of responsible partner for implementing the measure.
| Time for implementation | Information on the due date of implementation measure.
Not good status element, 2019 | FISH | Biological quality elements based on which the status assessment is given.
phytobenthos
macroinvertebrates
phytoplancton
macrophytes
| Phys-Chem, Ntot, Ptot, N-NH4 | Physical-Chemical ( e.g N, P) quality elements based on which the status assessment is given.

## Database EST
|  |  | Waterbody information |  |  |  | Status information 2019 |  |  |  |  | Pressures information 2019 |  |  | Existing measures from 2015-2021 river basin management plan
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
WB Code | WB Estonian name | Latvian name for transboundary WB | Transboundary WB code | Country | County | Municipality | Status 2019 | Not good status element, 2019 | Reason for the not good status | Monitoring year (latest or not monitored) | Status assessment confidence level | water use causing failure of GES/GEP | What causes the load: sector/water user | GAP (good status-status2019=gap; tons per year etc | The purpose of measure | Code of measure | Type of measure (administrative, technical, consulting, study) | supplementary, additional measure | Measure | Responsible partner for implementing the measure | not implemented / in progress / implemented | End of implementation | Type of measure (administrative, technical, consulting) | Code of measure | Measure | Description of measure | Responsible partner for implementing the measure
1155700_1 | Pärlijõgi_1 | Pērļupīte | LVEE1005 | Estonia | Võru | Rõuge | Poor | FISH | there are 2 dams without fishpasses | never monitored | 3 | Other obstacles causing hudromorphological pressures | recreation | Status class has to be improved by 2 classes. | Reducing pressure from hydrological and hydro-morphological changes on rivers with other obstacles/impoundments | VHP03 | Study | Additional | Technical measure for improvement of fish migration conditions/considering other alternatives fo Saarlase and Pärlijõe dams | Owner | Not implemented | 2021 | Technical | VHP04 | Demolishing the dam | Measure for opening the migration way for fish by demolishing the dam. | owner
1155700_2 | Pärlijõgi_2 |  |  | Estonia | Võru | Rõuge | Moderate | phytobenthos | dams fishpasses need improvement | never monitored | 3 | Other obstacles causing hudromorphological pressures | recreation | Status class has to be improved by 1 class. | Avoiding risk to water body from new and ongoing pressures | KE05 | Administrative | Supplementary | Additional supervision on water permits and other approvements on nutrients, hazardous substances and hydromorphological alterations in waterbody | Environmental Board, Municipality | Not implemented | 2021 | Technical | VHP09 | Improvement of existing fish passes | Measure for making improvements in fish passes in order to be more efficient | owner
1158000_1 | Vaidva_1* | Vaidava_1 | EELV1007 | Estonia | Võru | Rõuge | Moderate | FISH | dams | 2010 | 3 | Small HPP causing hydromorphological pressures | hydroenergy | Status class has to be improved by 1 class. | Reducing pressure from hydrological and hydro-morphological changes on rivers with other obstacles/impoundments | VHP05 | Study | Supplementary | Inspection of Vastse-Roosa fish pass | Environmental Board | Implemented | 2017 | - | - | - | - | -
1158000_2 | Vaidva_2* | Vaidava_2 | LVEE1008 | Estonia | Võru | Rõuge | Moderate | FISH | 2013 confirmation from dams inventory - good, fishpass done, but later years (2014-2017) it has not worked effectively because of the watermassive overflow and dam brokening issues. Fish expert has said that in 2017 the was no water lead to fishpass | 2017 | 3 | Small HPP causing hydro-morphological pressures | hydroenergy | Status class has to be improved by 1 class. | Avoiding risk to water body from new and ongoing pressures | KE05 | Administrative | Supplementary | Additional supervision on water permits and other approvements on nutrients, hazardous substances and hydromorphological alterations in waterbody | Environmental Board, Municipality | Continuous |  | Technical | VHP09 | Improvement of existing fish passes | Measure for making improvements in fish passes in order to be more efficient | owner
1012100_2 | Pedeli_2 | Pedele_2 | EELV1016 | Estonia | Valga | Valga | Moderate | FISH | dams Koiva/Gauja projekt (2013) | 2012 | 3 | Tther dams and obstacles creating hydro-morphological pressures | recreation | Status class has to be improved by 1 class. | Avoiding risk to water body from new and ongoing pressures | KE05 | Administrative | Supplementary | Additional supervision on water permits and other approvements on nutrients, hazardous substances and hydromorphological alterations in waterbody | Environmental Board, Municipality | Continuous |  | Study | VHP03 | Additional measure for improvement of fish migration conditions/considering other alternatives for Pedeli river dams | Additional measure for deciding whether to demolish the dams, build fish passes or to find some other alternative options | owner
2136600_1 | Aheru järv |  |  | Estonia | Valga | Valga | Moderate | Phys-Chem, phytoplancton | nutrients | 2016 | 3 | not known | not known | Status class has to be improved by 1 class. | Avoiding risk to water body from new and ongoing pressures | KE05 | Administrative | Supplementary | Additional supervision on water permits and other approvements on nutrients, hazardous substances and hydromorphological alterations in waterbody | Environmental Board, Municipality | Continuous |  | Study | KE03 | Study to clarify the outer and inner loads of the lake and to propose relevant measures | Study to clarify the outer and inner loads of the lake and to propose relevant measures
2155500_1 | Hino järv |  |  | Estonia | Võru | Rõuge | Moderate | macrophytes, macroinvertebrates | lake has species poverty situation, same type lakes are rich of species | 2017 | 3 | not known | not known | Status class has to be improved by 1 class. | Avoiding risk to water body from new and ongoing pressures | KE05 | Administrative | Supplementary | Additional supervision on water permits and other approvements on nutrients, hazardous substances and hydromorphological alterations in waterbody | Environmental Board, Municipality | Continuous |  | Study | KE03 | Study to clarify the outer and inner loads of the lake and to propose relevant measures | Study to clarify the outer and inner loads of the lake and to propose relevant measures
2144700_1 | Kirikumäe järv |  |  | Estonia | Võru | Võru | Moderate | Phys-Chem, macroinvertebrates | nutrients | 2017 | 3 | not known | not known | Status class has to be improved by 1 class. | Additional studies | KE03 | Administrative | Supplementary | Study to clarify the outer and inner loads of the lake and to propose relevant measures | Environmental Board | Implemented | 2019 | Administrative | KE05 | Limit activities that may have impact on lake nutrient content and hydromorphological changes. | Limit activities that may have impact on lake nutrient content and hydromorphological changes | Environmental Board, Municipality
2133700_1 | Köstrejärv |  |  | Estonia | Valga | Valga | Poor | macrophytes, macroinvertebrates | nutrients | 2018 | 3 | Accumulated pollution in sediments | historical pollution | Status class has to be improved by 2 classes. | There are several measures for Köstrejärv in the current programme of measures but there has been no information collection about implementing these measures. | [7 empty] | Technical |  | Complex method for remediation of lake | Complex method includes sediment dredging and macrophyte cutting and removal. Also sediment distribution and volum study is necessary
* - the border between Vaidva_1 and Vaidva_2 has been changed since the current river basin management plan and programme of measures was compiled. Previously the measure of Inspection on Vastse-Roosa fish pass was for Vaidva_1. Today the fish pass is on the Vaidva_2 water body.

## Database LAT
|  |  | Waterbody information |  |  |  | Status information 2019 |  |  |  |  | Pressures information 2019 |  |  | Existing measures from 2015-2021 river basin management plan
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
WB Code | WB Estonian name | WB Latvian name | Transboundary WB code | Country | County | Municipality | Status 2019 | Not good status element (last monitoring) | Reason for the not good status | Monitoring year (latest or not monitored) | Status assessment confidence level | water use causing failure of GES/GEP | What causes the load: sector/water user | GAP (good status-status2019=gap; tons per year etc) | The purpose of measure | Code of measure | Type of measure (administrative, technical, consulting, study) | supplementary, additional measure | Measure | Responsible partner for implementing the measure | not implemented / in progress | End of implementation | Type of measure (administrative, technical, consulting) | Code of measure | Measure | Description of measure | Responsible partner for implementing the measure | Time for implementation
E203 |  | Salainis |  | 4: Latvia; 5: Valkas; Status information 2019 7: moderate; Status information 2019 8: Ptot, Ntot, low Secchi-possible algae blooms; Status information 2019 9: Nutrient pollution - forestry; Status information 2019 10: 2013; Status information 2019 11: 3; Pressures information 2019 14: Status class has to be improved by 1 class.
E204 |  | Lūkumīša ezers |  | 4: Latvia; Status information 2019 7: moderate; Status information 2019 8: Secchi depth; Status information 2019 9: Nutrient pollution - forestry; Status information 2019 10: 2017; Status information 2019 11: 3; Pressures information 2019 14: Status class has to be improved by 1 class.; Existing measures from 2015-2021 river basin management plan 15: To improve the quality of lake water bodies; Existing measures from 2015-2021 river basin management plan 16: A7.6.; Existing measures from 2015-2021 river basin management plan 17: technical; Existing measures from 2015-2021 river basin management plan 18: supplementary; Existing measures from 2015-2021 river basin management plan 19: A7.6. Improving the functionality of the lake: mowing aquatic plants in the direction of prevailing winds and amplifying the wavy effect.; Existing measures from 2015-2021 river basin management plan 21: not implemented; Existing measures from 2015-2021 river basin management plan 22: 2021
E225 |  | Burtnieku ezers |  | Latvia | Alojas, Burtnieku, Mazsalacas |  | poor | All nutrients | Nutrient pollution - agriculture | 2018 | 3 |  | Diffuse and historical pollution | Status class has to be improved by 2 clases. | Minimize the impact of hydrological and morphological alterations and water status; To improve the quality of lake water bodies | A6.4. A7.3. A7.7 | technical (A6.4., A7.3.), study (A7.7.) | supplementary | A6.4. Keeping polders in a good condition (polder "Silzemnieki"); A7.3. cleaning of the lake - removal of plants and rubbish; A7.7. in plans of Nature protection agency of Latvia - defiining the size of area that needs to be free of aquatic vegetation for aquatic birds to thrive in lake Burtnieki |  | not implemented (A7.3., A7.7.); A6.4. In progress | 2020-07-01 | Technical measure |  | Complex measure - sediment dredging, macrophyte removal, biomanipulation | Biomanipulation - changing dominating fish species in lake to decrease amount of cyprinid fish species, and increase species of predatory fish. Measure can include both increased targeted fishing of cyprinid fish and artificial increase of piscivory fish populations. Macrophyte removal - cutting and removing macrophytes, such as common reed (Phragmites australis) from lake. It can be done by using aquatic mowers and collection containers attached to boats or by using specially designed aquatic weed harvesters. Macrophytes use available nutrients to grow, cutting them and removing from lake removes secondary useable nutrients - nutrients remaining in lake from decomposing plant matter. Sediment dredging - removal of sediments from the lake bed using dredger (excavator) or cutter and suction dredger would need to be used – appliances designed to dislodge sediments by cutting them, remove by suction through pipes and dispose in collection containers on ships.
E228 |  | Lielais Bauzis |  | Latvia | Kocēnu, Pārgaujas |  | moderate | Ntot,Ptot | Nutrient pollution - agriculture | 2011 | 3 |  |  | Status class has to be improved by 1 class. | Ensure reduction of pollution from forestry activities | A5.1. | technical | supplementary | A5.1 Environmentally friendly rebuilding or restoration of forest drainage systems to include environmentally friendly elements of drainage systems (sedimentation basins, two-stage drainage ditches, etc. Measures referred to in Annex 12 of Cabinet Regulation No. 600). |  | not implemented | 2021 | Technical measure |  | Complex measure - sediemnt dredging, biomanipulation, floating treatment wetlands, hypolimnetic withdrawal | Biomanipulation - changing dominating fish species in lake to decrease amount of cyprinid fish species, and increase species of predatory fish. Measure can include both increased targeted fishing of cyprinid fish and artificial increase of piscivory fish populations. Sediment dredging - removal of sediments from the lake bed using dredger (excavator) or cutter and suction dredger would need to be used – appliances designed to dislodge sediments by cutting them, remove by suction through pipes and dispose in collection containers on ships. Hypolimnetic withdrawal - removal of nutrient-enriched bottom layers of water from the lake through siphoning. Floating treatment wetlands - composed of an artificial platform that serves as a growing base for macrophytes. Nutrient removal through microbial transformation and uptake, macrophyte nutrient assimilation and removal from lake by macrophyte harvest.
G229 |  | Vija_1 |  | Latvia | Smiltenes, Strenču, Valkas |  | moderate | N-NH4 | Nutrient pollution -Agriculture. / Drainage - forestry / Nutrien pollution - forestry | 2013 | 3 |  | Hydromorphological pressures; N-NH4 | Status class has to be improved by 1 class. | Minimize the impact of hydrological and morphological alterations and water status; To improve the quality of lake water bodies | A6.1. | study (A6.1.), technical (A6.5.) | supplementary | A6.1. Survey of natural discharge regime in hydroelectrostation "Skripstu HES"; A6.5. cleaning of river from overgrowth of macrophytes and rubbish; mowing vegetation in meander shape in morphologically regulated parts of river |  | not implemented | 2021
G233 |  | Melnupe_2 | EELV1004 | 4: Latvia; 5: Alūksnes, Apes; Status information 2019 7: moderate; Status information 2019 9: Nutrient pollution; Status information 2019 10: 2016; Status information 2019 11: 1; Pressures information 2019 14: Status class has to be improved by 1 class.; Existing measures from 2015-2021 river basin management plan 23: study; Existing measures from 2015-2021 river basin management plan 25: Find a representative monitoring location.; Existing measures from 2015-2021 river basin management plan 26: According to the latest monitoring data, the quality of the Melnupe_2 is rated as moderate, but this is questionable due to the fact that the monitoring station is located in a location that is unlikely to objectively represent the quality of the entire waterbody. The proposed measure is therefore linked to the choice of site for the monitoring station.
G234 |  | Melnupe_1 |  | 4: Latvia; 5: Alūksnes, Apes; Status information 2019 7: moderate; Status information 2019 8: Ptot; Status information 2019 9: Nutrient pollution from agriculture / Drainage - Agriculture.; Status information 2019 10: 2017; Status information 2019 11: 3; Pressures information 2019 14: Status class has to be improved by 1 class.
G235 | Vaidva_2 | Vaidava_2 | LVEE1008 | Latvia | Alūksnes, Apes |  | moderate | Hydromorphological alterations (and biological response) | Dams, barrier and locks - hydropower / Nutrient pollution? | 2016 | 3 |  | Hydromorphological alterations (and biological response) | Status class has to be improved by 1 class. | To reduce the point pollution load on the waters | A1.3. | technical | supplementary | A1.3. Improving the efficiency of sewage treatment plants by providing additional waste water treatment in agglomerations with CE> 2000 which affects water bodies at risk. |  | In progress | 2021 | Technical measure. Technical measure. Technical +administrative measure. |  | For "Karva" HPP - demolishing dam or building a fish pass and implementing ecological flow For "Grūbe" HPP - demolishing am or building a fish pass and implementing ecological flow* | Demolishing a dam - includes complete removal of the dam and its structures. It aims restore fully natural continuity of river and remove all adverse effects of HPP dam on ecological status of river. Buildinga a fish pass - construction of an alternative way for migration of fish on rivers affected by dams or other obstacles. Case specific requirements for each fish pass should be established, depending on fish species of concern and specifics of river, such as depth, typology of river, as well as local specifics – availability of space, geology, etc. There are two main types of fish passes - natural type and technical type. Natural type fish passes require more space, as they mimic the river - artificial river bed is created. Technical type fish passes require less space. Problems are usually present with both upstream and downstream migration of fish, construction of two fish passes could be necessary to resolve both problems. Best available technological solutions must be applied based on scientific studies about fish pass efficiency rate, to enhance the effectivness. The measure also includes further maintenance of the fish pass in good working condition. Implementing ecological flow - addresses need for higher water level/discharge in river. Can be implemented by technical modification of sluice for storing less water above the dam and allowing sufficient amount of water to flow over the dam, to guarantee at least minimal good ecological conditions downstream. Fish pass or environmentally friendly HPP turbines can also be used to aid the flow. The measure requires a study to assess the ecological flow regime, as well as hydrological monitoring of the flow regime.
G241 |  | Gauja_6 |  | 4: Latvia; 5: Apes; Status information 2019 7: moderate; Status information 2019 9: Nutrient pollution - agriculture / Nutrient pollution - forestry; Status information 2019 10: 2016; Status information 2019 11: 3; Pressures information 2019 14: Status class has to be improved by 1 class.
G242 |  | Vizla_2 |  | 4: Latvia; 5: Apes, Smiltenes; Status information 2019 7: moderate; Status information 2019 9: Drainage - Agriculture; Status information 2019 10: 2013; Status information 2019 11: 3; Pressures information 2019 14: Status class has to be improved by 1 class.; Existing measures from 2015-2021 river basin management plan 15: Ensure reduction of pollution from forestry activities; Existing measures from 2015-2021 river basin management plan 16: A5.1.; Existing measures from 2015-2021 river basin management plan 17: technical; Existing measures from 2015-2021 river basin management plan 18: supplementary; Existing measures from 2015-2021 river basin management plan 19: A5.1 Environmentally friendly rebuilding or restoration of forest drainage systems to include environmentally friendly elements of drainage systems (sedimentation basins, two-stage drainage ditches, etc. Measures referred to in Annex 12 of Cabinet Regulation No. 600).; Existing measures from 2015-2021 river basin management plan 21: not implemented; Existing measures from 2015-2021 river basin management plan 22: 2021
G245 |  | Gauja_5 |  | 4: Latvia; 5: Alūksnes, Apes, Gulbenes; Status information 2019 7: moderate; Status information 2019 10: 2016; Status information 2019 11: 3; Pressures information 2019 14: Status class has to be improved by 1 class.
G301 |  | Salaca_2 |  | 4: Latvia; 5: Alojas, Mazsalacas, Salacgrīvas; Status information 2019 7: moderate; Status information 2019 9: Dams, barrier and locks - industry / Nutrient pollution - forestry / Nutrient pollution - agriculture; Status information 2019 10: 2017; Status information 2019 11: 3; Pressures information 2019 14: Status class has to be improved by 1 class.; Existing measures from 2015-2021 river basin management plan 23: Technical measure; Existing measures from 2015-2021 river basin management plan 25: Demolishing dam or building a fish pass.; Existing measures from 2015-2021 river basin management plan 26: Demolishing a dam - includes complete removal of the dam and its structures. It aims restore fully natural continuity of river and remove all adverse effects of HPP dam or other dam on ecological status of river. Buildinga a fish pass - construction of an alternative way for migration of fish on rivers affected by dams or other obstacles. Case specific requirements for each fish pass should be established, depending on fish species of concern and specifics of river, such as depth, typology of river, as well as local specifics – availability of space, geology, etc. There are two main types of fish passes - natural type and technical type. Natural type fish passes require more space, as they mimic the river - artificial river bed is created. Technical type fish passes require less space. Problems are usually present with both upstream and downstream migration of fish, construction of two fish passes could be necessary to resolve both problems. Best available technological solutions must be applied based on scientific studies about fish pass efficiency rate, to enhance the effectivness. The measure also includes further maintenance of the fish pass in good working condition.
G303SP |  | Salaca_3 |  | Latvia | Salacgrīvas |  | moderate | Ptot (occasionally) | Nutrient pollution | 2017 | 3 |  | Ptot (occasionally) | Status class has to be improved by 1 class. | To reduce the point pollution load on the waters A4 - Ensure the reduction of pollution from agricultural activities A6 - Samazināt hidroloģisko un morfoloģisko pārveidojumu ietekmi un ūdeņu stāvokli | A1.1.; A1.2.; A4.2., A6.3. | technical (A1.1.. A1.2., A4.2.), study (A6.3.) | supplementary | A1.1. Improving the efficiency of waste water treatment plants by providing additional waste water treatment in agglomerations with CE> 2000 affecting water bodies at risk; A1.2. Improvement of the functioning of centralized wastewater collection systems by providing actual connections and extending networks in agglomerations with CE> 2000 affecting water bodies at risk; A4.2. Environmentally friendly rebuilding and restoration of agricultural drainage systems, including environmentally friendly elements of drainage systems (sedimentation basins, two-stage drainage ditches, etc. Measures referred to in Annex 12 of Cabinet Regulation No. 600); A6.3. Implement the established action plans and priority "mitigating" measures to reduce the negative impacts of ports. |  | not implemented | 2021
G304 |  | Iģe_1 |  | 4: Latvia; 5: Alojas, Kocēnu, Limbažu, Mazsalacas; Status information 2019 7: moderate; Status information 2019 8: Nutriens from agriculture; Status information 2019 9: Nutrient pollution from agriculture / Drainage - Forestry; Status information 2019 10: Never monitored; Status information 2019 11: 3; Pressures information 2019 14: Status class has to be improved by 1 class.
G306 |  | Salaca_1 |  | Latvia | Alojas, Burtnieku, Mazsalacas |  | moderate |  | Dams, barrier and locks - unknown / Drainage - Agriculture | 2013 | 3 |  |  | Status class has to be improved by 1 class. | To reduce the point pollution load on the waters | A1.2. | technical | supplementary | A1.2. Improvement of the functioning of centralized wastewater collection systems by providing actual connections and extending networks in agglomerations with CE> 2000 affecting water bodies at risk; |  | not implemented | 2021 | Technical measure |  | Demolishing dam or building a fish pass. | Demolishing a dam - includes complete removal of the dam and its structures. It aims restore fully natural continuity of river and remove all adverse effects of HPP dam or other dam on ecological status of river. Buildinga a fish pass - construction of an alternative way for migration of fish on rivers affected by dams or other obstacles. Case specific requirements for each fish pass should be established, depending on fish species of concern and specifics of river, such as depth, typology of river, as well as local specifics – availability of space, geology, etc. There are two main types of fish passes - natural type and technical type. Natural type fish passes require more space, as they mimic the river - artificial river bed is created. Technical type fish passes require less space. Problems are usually present with both upstream and downstream migration of fish, construction of two fish passes could be necessary to resolve both problems. Best available technological solutions must be applied based on scientific studies about fish pass efficiency rate, to enhance the effectivness. The measure also includes further maintenance of the fish pass in good working condition.
G308 |  | Jogla |  | 4: Latvia; 5: Alojas, Limbažu; Status information 2019 7: moderate; Status information 2019 8: Ptot; Status information 2019 9: Point source - non IED plants / Nutrients pollution; Status information 2019 10: 2018; Status information 2019 11: 3; Pressures information 2019 14: Status class has to be improved by 1 class.
G310 |  | Rūja_4 |  | 4: Latvia; 5: Burtnieku, Mazsalacas, Naukšēnu, Rūjienas; Status information 2019 7: moderate; Status information 2019 9: Drainage - Forestry / Drainage - Agriculture; Status information 2019 10: 2018; Status information 2019 11: 3; Pressures information 2019 14: Status class has to be improved by 1 class.
G313 |  | Rūja_2 |  | 4: Latvia; 5: Naukšēnu, Rūjienas; Status information 2019 7: moderate; Status information 2019 9: Drainage - Agriculture; Status information 2019 10: 2013; Status information 2019 11: 3; Pressures information 2019 14: Status class has to be improved by 1 class.
G315 |  | Ķire |  | 4: Latvia; 5: Naukšēnu, Rūjienas, Valkas; Status information 2019 7: moderate; Status information 2019 9: Drainage - Agriculture; Status information 2019 10: 2012; Status information 2019 11: 3; Pressures information 2019 14: Status class has to be improved by 1 class.
G317 | Pedeli_2 | Pedele_2 | LVEE1016 | Latvia | Valkas |  | moderate | Biological response to hydromorphological alterations | Dams, barrier and locks - hydropower | 2015 | 3 |  | Biological response to hydromorphological alterations | Status class has to be improved by 1 class. | To reduce the point pollution load on the waters; Minimize the impact of hydrological and morphological alterations and water status | A.1.2., A6.5. | technical | supplementary | A1.2. Improvement of the functioning of centralized wastewater collection systems by providing actual connections and extending networks in agglomerations with CE> 2000 affecting water bodies at risk; A6.5. Watercourse cleaning (controlling the degree of overgrowth of aquatic plants, decontamination of water), clean-up of the coasts in accordance with good practice, with the aim of improving the ecological quality of the water; meandering of macrophytes in regulated river sections. |  | A1.2. In progress; not implemented (A6.5.) | 2022-11-01 | Technical measure |  | For Kalndzirnavu HPP - demolishing a dam. For Dzirnavnieku HPP - demolishing a dam. | Demolishing a dam - includes complete removal of the HPP dam and its structures. It aims restore fully natural continuity of river and remove all adverse effects of HPP dam on ecological status of river.
G320 |  | Acupīte_2 |  | 4: Latvia; 5: Naukšēnu, Valkas; Status information 2019 7: moderate; Status information 2019 9: Drainage - Agriculture; Status information 2019 10: 2011; Status information 2019 11: 3; Pressures information 2019 14: Status class has to be improved by 1 class.
G322 |  | Briede_1 |  | Latvia | Kocēnu, Limbažu, Pārgaujas |  | moderate | Nutrients, hymo alterations | 1. Dams, barrier and locks - hydropower. 2. Dams, barrier and locks - unknown / Nutrients runoff - Agriculture | 2018 | 3 |  |  | Status class has to be improved by 1 class. | Ensure reduction of pollution from forestry activities | A5.1. | technical | supplementary | A5.1 Environmentally friendly rebuilding or restoration of forest drainage systems to include environmentally friendly elements of drainage systems (sedimentation basins, two-stage drainage ditches, etc. Measures referred to in Annex 12 of Cabinet Regulation No. 600). |  | not implemented | 2021 | Technical measure |  | For "Kārlīšu" HPP - demolishing dam or building a fish pass and implementing ecological flow. For "Sviluma" impoundment lake - demolishing dam or building fish pass. For impoundment lake on river Briede - | Demolishing a dam - includes complete removal of the dam and its structures. It aims restore fully natural continuity of river and remove all adverse effects of HPP dam or other dam on ecological status of river. Buildinga a fish pass - construction of an alternative way for migration of fish on rivers affected by dams or other obstacles. Case specific requirements for each fish pass should be established, depending on fish species of concern and specifics of river, such as depth, typology of river, as well as local specifics – availability of space, geology, etc. There are two main types of fish passes - natural type and technical type. Natural type fish passes require more space, as they mimic the river - artificial river bed is created. Technical type fish passes require less space. Problems are usually present with both upstream and downstream migration of fish, construction of two fish passes could be necessary to resolve both problems. Best available technological solutions must be applied based on scientific studies about fish pass efficiency rate, to enhance the effectivness. The measure also includes further maintenance of the fish pass in good working condition. Implementing ecological flow - addresses need for higher water level/discharge in river. Can be implemented by technical modification of sluice for storing less water above the dam and allowing sufficient amount of water to flow over the dam, to guarantee at least minimal good ecological conditions downstream. Fish pass or environmentally friendly HPP turbines can also be used to aid the flow. The measure requires a study to assess the ecological flow regime, as well as hydrological monitoring of the flow regime.
G325 |  | Blusupīte |  | 4: Latvia; 5: Salacgrīvas; Status information 2019 7: moderate; Status information 2019 9: Nutrients pollution - Agriculture /Drainage - Forestry; Status information 2019 10: 2016; Status information 2019 11: 3; Pressures information 2019 14: Status class has to be improved by 1 class.
G334 | Vaidva_2 | Vaidava_1 | EELV1007 | 4: Latvia; 5: Alūksnes; Status information 2019 7: moderate; Status information 2019 10: Never monitored; Status information 2019 11: 3; Pressures information 2019 14: Status class has to be improved by 1 class.